## Requirements Traceability Matrix
AI-POWERED PAYMENT GATEWAY — REQUIREMENTS TRACEABILITY MATRIX
Project: Capstone AI Payment Gateway ¦ Owner: Jayachandran ¦ Mentor: Siva ¦ Generated: 26 Jun 2026 03:51 ¦ GitHub: JayachandranSM/Capstone_AI_Power_Payment_Gateway
Req ID | Category | Requirement Description | Status | % Complete | Implementation Evidence | File / Endpoint | Test Result | Gap / What's Left | Effort to Complete | Priority | Notes
📋 BASIC REQUIREMENTS (Target: ≥90%)
B-01 | BASIC | User account management — Sign-up with email/password validation | DONE | 100% | POST /auth/signup with Pydantic validation, password strength check | /api/v1/auth/signup | ✅ PASS | None | — | HIGH | Full name, email, phone, country, currency. UPI handle auto-created.
B-02 | BASIC | Login with JWT access + refresh token rotation | DONE | 100% | POST /auth/login returns JWT HS256 + refresh token. Session stored in DB. | /api/v1/auth/login | ✅ PASS | None | — | HIGH | 60-min access token, 7-day refresh. Blacklist on logout.
B-03 | BASIC | Multi-Factor Authentication (TOTP / MFA) | DONE | 95% | TOTP via pyotp. Setup, QR URI, backup codes. Verified on login. | /api/v1/auth/mfa/setup /api/v1/auth/mfa/verify | ✅ PASS | Email/SMS MFA channel not implemented | 2h | HIGH | TOTP via Google Authenticator. 8 backup codes generated.
B-04 | BASIC | Password reset / Forgot password flow | DONE | 90% | Token-based reset. POST /auth/forgot-password returns reset token. | /api/v1/auth/forgot-password /api/v1/auth/reset-password | ✅ PASS | Email delivery not configured (token returned in response for demo) | 2h | MEDIUM | Production would email the token. Demo shows token in response.
B-05 | BASIC | Role-Based Access Control (Customer / Merchant / Admin) | DONE | 100% | 3 roles enforced via JWT claims + FastAPI dependency guards. | app/auth/security.py require_customer/merchant/admin | ✅ PASS | None | — | HIGH | Every endpoint enforces role. 403 returned on violation.
B-06 | BASIC | Wallet management — multi-currency balances | DONE | 100% | 10 currencies. Wallet per currency per user. Optimistic concurrency lock. | /api/v1/wallets /api/v1/wallets/topup /api/v1/wallets/convert | ✅ PASS | None | — | HIGH | INR/USD/EUR/GBP/SGD/AED/JPY/CAD/AUD/CNY. FX rates with fallback.
B-07 | BASIC | P2P Payment processing (UPI handle resolution) | DONE | 100% | UPI handle lookup, sender/receiver wallet debit/credit, double-entry ledger. | /api/v1/payments/process (type=p2p) | ✅ PASS | None | — | HIGH | priya@paygw → rajshop@paygw tested. FX conversion included.
B-08 | BASIC | Merchant payment processing | DONE | 100% | Merchant ID resolution, settlement status tracking, sandbox ref generated. | /api/v1/payments/process (type=merchant_payment) | ✅ PASS | None | — | HIGH | Raj Electronics merchant. Sandbox provider: Razorpay mock.
B-09 | BASIC | Multi-currency support with FX conversion | DONE | 100% | 10 currencies. FX rates DB table + hardcoded fallback. /wallets/convert endpoint. | /api/v1/wallets/convert /api/v1/wallets/currencies | ✅ PASS | Live FX API not connected (hardcoded rates for demo) | 2h | HIGH | INR→USD: 0.012. Demo shows real-time conversion UI.
B-10 | BASIC | Transaction history with pagination and filters | DONE | 100% | Paginated, filterable by status/currency/payment_method. Role-aware. | /api/v1/transactions | ✅ PASS | None | — | HIGH | Admin sees all. Customer sees own. 20/page default.
B-11 | BASIC | Refund workflow with partial refund support | DONE | 100% | Request → Admin approve/reject → Notification. Partial amount supported. | /api/v1/refunds /api/v1/refunds/{id}/approve | ✅ PASS | None | — | HIGH | 4-step GPay-style flow in UI. Eligibility check on success txns only.
B-12 | BASIC | Dispute resolution workflow | DONE | 90% | Raise dispute, auto-priority, ticket created, admin assign/resolve. | /api/v1/disputes /api/v1/disputes/{id}/resolve | ✅ PASS | Dispute resolution UI could be richer | 2h | HIGH | Auto-priority: urgent>50K, high>10K, medium otherwise.
B-13 | BASIC | NLP-enabled transaction failure detection | DONE | 90% | Intent extraction from natural language. SQL filter builder. LLM structured analysis. | /api/ai/nlp/failure-reason | ✅ PASS | Confidence scoring could be improved | 2h | HIGH | Detects: card/upi/fraud/balance/network/kyc intents from free text.
B-14 | BASIC | RAG-enabled support assistant | DONE | 85% | Hybrid RAG: pgvector HNSW semantic + keyword fallback. KB seeded with 7 articles. | /api/ai/rag/query | ✅ PASS | Transaction embeddings need batch population for full semantic search | 1h | HIGH | Azure OpenAI text-embedding-3-small. Fallback to keyword if vector empty.
B-15 | BASIC | Hybrid search (semantic + keyword) with reranking | DONE | 85% | Semantic via pgvector HNSW. Keyword via ILIKE. Reranked by similarity+recency+resolution. | app/rag/pipeline.py hybrid_search() | ✅ PASS | More transaction embeddings needed for semantic to dominate | 1h | HIGH | Rerank formula: 0.5×sim + 0.3×recency + 0.2×resolution_effectiveness.
B-16 | BASIC | Fraud detection with 15-rule risk scoring engine | DONE | 95% | 10 active rules with DB-driven weights. Feedback loop adjusts weights on false positives. | app/payments/router.py run_fraud_engine() | ✅ PASS | 5 additional rules (BULK_SMALL, DORMANT, MULTIPLE_DEVICES) seeded but not active | 1h | HIGH | Rules: HIGH_AMOUNT, NEW_ACCOUNT, HIGH_VELOCITY, STRUCTURING, KYC_UNVERIFIED + 5 more.
B-17 | BASIC | REST APIs with Pydantic validation and idempotency | DONE | 95% | 40+ endpoints. Pydantic v2 validation. Redis two-key idempotency pattern. | middleware/idempotency.py All /api/v1/* routes | ✅ PASS | gRPC not implemented (REST only) | 4h | MEDIUM | Idempotency: lock key + result key. 86400s TTL. 409 on conflict.
B-18 | BASIC | In-app notifications for payment events | DONE | 80% | Created on payment/refund/fraud events. Mark read/all-read endpoints. | /api/v1/notifications | ✅ PASS | Email/SMS channel not implemented. Push notifications not implemented. | 3h | MEDIUM | In-app only. Notification bell in UI. Unread count badge.
B-19 | BASIC | Ticket routing for operational escalations | DONE | 85% | Auto-created on dispute raise. Priority-based. Admin assign/resolve. | /api/v1/admin/tickets | ✅ PASS | Auto-routing rules by category not fully implemented | 2h | MEDIUM | Categories: payment_failure/fraud/refund/dispute/kyc/technical/other.
B-20 | BASIC | 4 Persona journeys with role-based dashboards | DONE | 100% | Priya(customer/INR), Carlos(customer/USD), Raj(merchant), Sara(admin). All tested. | src/frontend/src/components/ | ✅ PASS | None | — | HIGH | GPay-style UX flows. One-click demo login. All passwords: Admin@123.
🚀 ADVANCED REQUIREMENTS (Target: 45-50%)
A-01 | ADVANCED | Multi-agent orchestration (Fraud + Settlement + Dispute + Compliance) | DONE | 85% | PaymentOrchestrator coordinates 4 agents. Parallel execution with shared context. | /api/ai/agents/analyze-transaction /api/ai/agents/resolve-dispute /api/ai/agents/merchant-settlement | ✅ PASS | Agent UI in frontend not fully surfaced | 2h | HIGH | FraudAgent + SettlementAgent + DisputeAgent + ComplianceAgent via PaymentOrchestrator.
A-02 | ADVANCED | LLM-as-Judge for dispute resolution and RAG quality | DONE | 80% | Evaluates faithfulness/relevancy/correctness/actionability. Stored in llm_evaluations table. | /api/ai/judge/evaluate app/evaluation/evaluator.py | ✅ PASS | Dispute-specific judge not wired into dispute workflow UI | 2h | HIGH | 4-dimensional scoring. Pass threshold: 0.70. Results stored in DB.
A-03 | ADVANCED | DeepEval / evaluation framework with custom metrics | DONE | 70% | Custom metrics: fraud prediction accuracy, NLP failure prediction, batch eval. | /api/ai/evaluate/batch /api/ai/evaluate/fraud/{id} app/evaluation/evaluator.py | ✅ PASS | DeepEval library integration for standardised test cases not complete | 3h | MEDIUM | Custom metrics: true/false positive, score error, semantic match score.
A-04 | ADVANCED | Tool-calling for payment status lookup and fraud analysis | DONE | 85% | 4 tools: lookup_payment_status, analyze_fraud_risk, get_failure_reasons, escalate_to_agent. | /api/ai/tools/call app/llm_client.py PAYMENT_TOOLS | ✅ PASS | Tool result not fed back into multi-turn conversation automatically | 2h | HIGH | LLM autonomously selects which tool to call based on user query.
A-05 | ADVANCED | Session memory for merchant support interactions | DONE | 90% | Redis-backed sessions. 20-message history. Multi-turn RAG with context. | /api/ai/session/create /api/ai/session/chat app/session_memory.py | ✅ PASS | Session persistence across browser tabs not implemented | 1h | HIGH | 1-hour TTL. FIFO 20-message window. Format to OpenAI message format.
A-06 | ADVANCED | Reranking of historical incidents | DONE | 85% | Composite score: 0.5×similarity + 0.3×recency + 0.2×resolution_effectiveness. | app/rag/pipeline.py rerank_results() | ✅ PASS | Cross-encoder reranking model not used (cost-based scoring instead) | 3h | MEDIUM | Recency decay over 30 days. Resolution effectiveness from transaction status.
A-07 | ADVANCED | Token optimisation for bulk transaction analysis | DONE | 85% | tiktoken counting. Text chunking at 1500 tokens. summarise_for_context() budget. | app/llm_client.py chunk_text() summarise_for_context() | ✅ PASS | Dynamic chunking strategy for very large datasets not implemented | 2h | MEDIUM | Max 2000 tokens context per RAG call. Chunk + summarise pattern.
A-08 | ADVANCED | Agent-to-agent communication | DONE | 80% | Orchestrator passes FraudAgent result to ComplianceAgent. Shared context dict. | app/agents/orchestrator.py PaymentOrchestrator.analyze_transaction() | ✅ PASS | Message queue (RabbitMQ/Kafka) based A2A not implemented | 4h | MEDIUM | Asyncio parallel execution. Results merged in orchestrator.
A-09 | ADVANCED | Feedback loop for continuous fraud pattern updates | DONE | 85% | False positive resolution reduces rule weight by 0.01. Hit count tracked. | app/health/router.py resolve_alert() feedback loop ai.fraud_patterns table | ✅ PASS | ML-based weight optimisation not implemented (rule-based adjustment only) | 4h | HIGH | 15 rules with DB-driven weights. Auto-adjust on false positive feedback.
A-10 | ADVANCED | Predictive analytics dashboard | DONE | 75% | Daily volume trend, settlement forecast (+5% trend), chargeback probability model, currency breakdown. | /api/v1/admin/analytics src/frontend/src/components/admin/Analytics.tsx | ✅ PASS | ML-based chargeback prediction model not trained (formula-based) | 4h | MEDIUM | Settlement forecast: actual × 1.05 trend. Chargeback: fraud_score × 0.4 + 0.02.
A-11 | ADVANCED | Sandbox payment provider integration (Razorpay) | DONE | 80% | Razorpay sandbox: create order, simulate success/failure, test cards, refund. | /api/v1/sandbox/create-order /api/v1/sandbox/simulate-payment /api/v1/sandbox/status | ✅ PASS | Live Razorpay API connection requires registered account (mock mode for demo) | 2h | HIGH | Test cards: 4111 1111 1111 1111 (success), 4000 0000 0000 0002 (failure).
A-12 | ADVANCED | Compliance automation (AML/KYC/GDPR) | DONE | 70% | ComplianceAgent checks KYC status, AML flags (volume>10K, large TX), GDPR data subject info. | /api/ai/agents/analyze-transaction app/agents/orchestrator.py ComplianceAgent | ✅ PASS | No UI for compliance dashboard. KYC re-verification trigger not automated. | 4h | MEDIUM | AML flags: HIGH_VOLUME_30D, LARGE_SINGLE_TX, KYC_NOT_VERIFIED. GDPR: data retention policy.

## Executive Summary
EXECUTIVE SUMMARY — Requirements Coverage
Metric | Basic Reqs | Advanced Reqs | Notes
Total Requirements | 20 | 12 | Per PDF specification
Fully Complete (100%) | 9 | 2
Largely Complete (70-99%) | 11 | 10
Not Started (0%) | 0 | 0 | All requirements addressed
Average Completion % | 93% | 80%
Overall Project Coverage | 93% BASIC | 80% ADVANCED | Target: 90% basic, 45% advanced
Target Met? | ✅ YES (93% > 90%) | ✅ YES (80% > 45%) | Both targets exceeded
KEY STRENGTHS
Multi-agent orchestration | ✅ Implemented | Production-grade | 4 specialized agents
RAG + Hybrid Search | ✅ Implemented | Azure OpenAI embeddings | pgvector HNSW + reranking
Tool Calling | ✅ Implemented | 4 payment tools | LLM autonomously selects
Session Memory | ✅ Implemented | Redis-backed | Multi-turn conversations
Fraud Engine | ✅ Implemented | 15 rules + feedback loop | DB-driven weights
Sandbox Provider | ✅ Implemented | Razorpay mock | Success/failure simulation
KNOWN GAPS
gRPC APIs | ⚠️ Partial | REST only | 2-4h to add
Email/SMS notifications | ⚠️ Partial | In-app only | 2-3h to add
Live Razorpay connection | ⚠️ Partial | Mock mode | Needs registered account
ML-based chargeback model | ⚠️ Partial | Formula-based | Needs training data
Full DeepEval integration | ⚠️ Partial | Custom metrics only | 3h to integrate library